## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2021-09-13 | 35 | 2021-10-17 | 57 | 68 | Released | 2014-04-09 | Lograr transacciones de datos | 119.3%
2 | 2021-10-18 | 21 | 2021-11-07 | 26 | 42 | Released | 2014-04-30 | Cumplir con reglas de negocio para extraccion de información | 161.5%
3 | 2021-11-08 | 0 | 2021-11-07 | 0 | 0 | Planned | 2014-05-20 | Cumplir con entregables de trabajo de grado
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
0 | 2021-09-06 | 5 | 2021-09-12 | 3 | 4 | Ongoing | 2014-03-12 | Especificación y desarrollo de proyecto | 1 | 33.33%
1 | 2021-09-13 | 7 | 2021-09-19 | 3 | 4 | Released | 2014-03-12 | Especificación y desarrollo de prototipo | 1 | 33.33%
2 | 2021-09-13 | 14 | 2021-09-26 | 28 | 37 | Released | 2014-03-26 | Especificación y desarrollo de prototipo | 1 | 32.14%
3 | 2021-09-09 | 14 | 2021-09-22 | 26 | 27 | Released | 2014-04-09 | Especificación y desarrollo de prototipo | 1 | 3.846%
4 | 2021-09-10 | 14 | 2021-09-23 | 26 | 26 | Released | 2014-04-23 | Especificación y desarrollo de prototipo | 2 | 0%
5 | 2021-09-11 | 7 | 2021-09-17 | 0 | 16 | Planned | 2014-05-07 | Pruebas de usabilidad, documentación, correcciones | 2 | #DIV/0!
6 | 2021-09-12 |  | #VALUE! | 0 |  | Planned | 2014-05-14 | Correcciones Memoria TG | 3
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | #VALUE!
|  |  | Total Size | 83 | 110
Formulas:
Start = IF(OR(B17="",[Incr.]=""),"",B17)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Product Backlook | Ongoing | 3 | 0 | 5 | Planificación | Se realizó según la planeación | Sin Impacto
2 | Repositorio (GitHub) | Done | 8 | 0 | 5 | Planificación | Se realizó según la planeación | Sin Impacto
3 | Gestión de configuración | Planned | 20 | 0 | 4 | Planificación | Se realizó según la planeación | Sin Impacto
4 | Historias de usuario a desarrollar para Sprint 1 | Ongoing | 13 | 0 | 4 | Planificación | Se realizó según la planeación | Sin Impacto
5 | Configuración DevOps | Ongoing | 13 | 0 | 3 | Planificación | Se realizó según la planeación | Sin Impacto
6 | Mookups | Ongoing | 13 | 0 | 2 | Planificación | Se realizó según la planeación | Sin Impacto
7 | UML Casos de uso | Done | 13 | 0 | 2 | Planificación | Se realizó según la planeación | Sin Impacto
8 | Agregar archivo Documentación de software IEEE | Done | 13 | 0 | 1 | Planificación | Se realizó según la planeación | Sin Impacto
9 | Realizar plan de pruebas de usuario, ejecución de pruebas y documentación | Ongoing | 8 | 6 | 2 | Proyecto
10 | Realizar página TG y correcciones | Ongoing | 8 | 6 | 2 | Académica
11 | Correcciones y finalización Memoria TG | Planned | 10 | 7 | 4 | Académica
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.